## Tasks
Title | Description | Status | Priority | Progress | Start Date | Due Date | Dependency Task | Dependency Details | Dependency Status | Dependency Owner | Final Comments
Header design | Build the responsive site header with sticky navigation | In Progress | High | 40% | 2026-06-01 | 2026-06-15 | Brand guidelines sign-off | Need final logo + colour tokens before final pass | In Review | Marketing | Awaiting brand sign-off; once approved, can wrap in a day.
Footer revamp | Replace legacy footer with the new component | Pending | Medium | 0% | 2026-06-10 | 2026-06-20
Homepage hero animation | Implement scroll-triggered hero section | Pending | High | 0% | 2026-06-12 | 2026-06-22 | Hero copy approval | Awaiting final hero copy from content team | Pending | Content | Blocked until content team finalises copy.
SEO audit fixes | Apply remediations from the Q2 SEO audit | Completed | Medium | 100% | 2026-05-20 | 2026-05-30 |  |  |  |  | Done — all audit items addressed.
Form validation refactor | Move all forms to react-hook-form + zod | In Progress | Critical | 65% | 2026-05-28 | 2026-06-10 | API error contract | Backend needs to standardise validation error payload | In Progress | Backend | Frontend pieces done; integration paused on backend contract.
Sitemap & robots.txt | Generate and ship the production sitemap and robots | Pending | Low | 0% | 2026-06-15 | 2026-06-25